## Project1
section | id | depends_on | start | end | deadline | est_duration_init | est_duration | status | resource | task | progress
Section1 |  |  | TODAY |  |  | 1 | 1 |  | A | Task1 | 50
Section1 |  | PREVIOUS |  |  |  | 15 | 15 |  | B | Task2 | 50
Section2 |  |  | 2019-11-17 |  |  | 2 | 2 | await | A | Task3 | 0

## Project2
section | id | depends_on | start | end | deadline | est_duration_init | est_duration | status | resource | task | progress
Section1 |  |  | TODAY |  |  | 1 | 1 | unscheduled | D | Task1 | 100
Section1 |  | PREVIOUS |  |  |  | 3 | 3 |  | D | Task2 | 100
Section2 |  |  | TODAY |  |  | 2 | 2 |  | E | Task3 | 0